Payments Operations Automation

Program Proposal

Automating the back-office payment lifecycle across

RTP · Fedwire · ACH · Stablecoin · SWIFT

Prepared for: Payments Steering Committee

Audience: Engineering · Leadership · Compliance · Operations

Status: Draft v0.1

Confidential — internal design document. Figures and scenarios are illustrative.

# Contents

# 1. Executive summary

This proposal sets out a program to automate the bank’s back-office payment operations across five rails — RTP, Fedwire, ACH, stablecoin, and SWIFT. Today these rails run on separate, largely manual processes, each re-keying, repairing, screening, and reconciling in its own way; cost and headcount scale with payment volume, and compliance is applied unevenly rail by rail.

The program replaces that with a single, exception-based operating model built on one real-time screening spine and reconciled to the settlement position per rail. People move from re-keying payments to clearing alerts and exceptions. Sanctions screening, AML monitoring, and SAR/FinCEN filing are designed in as first-class capabilities — the bank files as the obligated institution — rather than bolted onto each rail.

Delivery is sequenced into four waves: a shared foundation first, then ACH as the pilot, then the real-time irrevocable rails (RTP and Fedwire), then the cross-border and on-chain rails (SWIFT and stablecoin). Stablecoin, the most novel rail, begins discovery early because it depends on net-new custody, analytics, and an evolving regulatory framework.

The ask: approve the program and operating model, fund the Wave 0 foundation, and authorize Phase 0 calibration to convert the indicative roadmap into a data-driven sequence.

# 2. The opportunity

As an intermediary, the bank sits between its customers and the payment networks, running every payment on both an outbound (origination) and inbound (receipt) path. The current state has three structural problems:

- Rail silos. Each rail duplicates capture, repair, screening, and reconciliation, so effort and cost grow with volume rather than with the number of genuine exceptions.

- Uneven compliance. Sanctions screening and AML monitoring vary by rail, creating both risk and high false-positive manual load — acute on instant, irrevocable rails where there is no review window.

- Late reconciliation. With no single ledger equivalent, breaks against the settlement and nostro positions surface late and are worked manually.

Automation that simply speeds the current silos misses the point. The opportunity is to change the operating model so the cost base scales with exceptions, not with payment volume.

# 3. Structural position

The bank is an intermediary between customers (originators and beneficiaries) and the payment rails. Two variables shape every rail: direct vs indirect participation, and push vs pull. Unlike a securities back office, there is no single golden ledger; the integrity anchor is the settlement / nostro position per rail, which every flow must reconcile to. And every payment, on either path, passes a mandatory screening gate — in payments, compliance is the spine, not a side process.

# 4. Proposed approach

Three principles hold the design together:

- Exception-based. Straight-through on the happy path; people touch only what breaks or what compliance flags. Headcount scales with exceptions and alerts, not volume.

- Screen once, screen well. Sanctions and AML are shared, real-time services every rail calls — not six rail-specific implementations — with false positives engineered down as a first-class cost.

- Reconcile to the settlement position. Every flow reconciles to the settlement / nostro position per rail; for stablecoin this extends to on-chain ↔ off-chain.

Delivery philosophy: integrate first (real APIs, ISO 20022, SWIFT, on-chain), use RPA only to bridge operator or correspondent portals with no feed, and retire each bridge on a defined path. Controls are embedded in-flow, not reconstructed after the fact.

# 5. Scope

Five rails are in scope, spanning the full range of payment types, plus the shared foundation. Fixed scope keeps the program focused; the rails differ enough that each needs its own treatment.

| Rail | Settlement | Speed | Reversibility | Lead automation |
| --- | --- | --- | --- | --- |
| RTP | Prefunded RTGS | Instant 24/7 | Irrevocable | Real-time screening, prefunding |
| Fedwire | RTGS | Same-day | Final | STP repair, real-time screening |
| ACH | Deferred net | Same/next-day | Returns/reversals | Returns & NOC, batch exceptions |
| Stablecoin | On-chain | Near-instant 24/7 | Irreversible | On-chain recon, wallet screening |
| SWIFT | Nostro/vostro | Variable | Recall (not guaranteed) | Repair, nostro recon, gpi |

# 6. Target operating model

The operating model shifts on every dimension: from rail-siloed teams to function-based teams (processing & repair, screening/compliance operations, investigations, reconciliation & liquidity); from point-to-point connections to a payment hub with a shared screening service and golden reference data; and from volume-linked to exception-linked staffing. The defining metric set is shared across rails — STP rate, screening false-positive rate, repair rate, returns rate, settlement breaks, investigation aging, and cost per payment.

In one line: from rail-siloed, volume-linked, screen-everywhere operations — to a single exception-based lifecycle with one real-time screening spine, reconciled to the settlement position, where people clear alerts and exceptions rather than re-key payments.

# 7. Compliance architecture (AML, SAR, FinCEN)

Because the bank files as the obligated institution, compliance is engineered as two distinct capabilities and carried per rail — not bolted on.

- Sanctions screening (blocking, real-time). A shared service screens every payment pre-execution against sanctions lists; on irrevocable rails it must clear pre-send, within a latency budget, with no hold-and-review fallback.

- AML monitoring + SAR/FinCEN case management. Behavioral monitoring raises alerts that drive investigations and produce filings: SAR decisioning and e-filing to the FinCEN BSA system, the 30/60-day clock, continuing SARs, CTRs, 314(a)/(b), with SAR confidentiality and retention.

Each rail carries its own AML/SAR/FinCEN block, because the obligations trigger differently:

| Rail | Rail-specific AML / SAR / FinCEN emphasis |
| --- | --- |
| ACH | Structuring across batches, mule networks, unauthorized-return signals; BSA Travel Rule completeness. |
| Fedwire | Pre-send high-value risk scoring; Travel Rule data on transmittals; nested-correspondent exposure. |
| RTP | Real-time, pre-send AML scoring; APP/scam typologies; 24/7 case coverage and SAR-clock management. |
| SWIFT | Cross-border typologies, multi-hop party screening, information-stripping detection, correspondent due diligence. |
| Stablecoin | Wallet/address analytics, crypto VASP-to-VASP Travel Rule, source-of-funds on ramps. |

Note: regulatory timers and thresholds are flagged for confirmation against current rules, as several are subject to change.

# 8. Delivery roadmap

Initiatives are scored on volume × risk × feasibility and sequenced into four waves, with the foundation first because nothing is straight-through until it exists.

| Wave | Focus | Rationale |
| --- | --- | --- |
| Wave 0 | Foundation (F1–F6) | Screening spine, golden data, payment hub, exceptions desk, reconciliation, AML/SAR. |
| Wave 1 | ACH (pilot) | Highest volume, most standardized, reversible — proves the model and the foundation. |
| Wave 2 | RTP + Fedwire | Real-time, irrevocable rails — proves pre-send screening/AML at scale; most risk reduced. |
| Wave 3 | SWIFT + Stablecoin | Cross-border and on-chain — hardest and longest-lead; stablecoin discovery starts in Wave 1. |

Critical path: the screening spine — F1 (sanctions/reference data) → F2 (shared screening) → real-time screening → the instant rails. On irrevocable rails screening must be both fast and accurate before any automation is safe, so this chain gates Wave 2.

# 9. Build requirements

Requirements are specified as testable functional, data, integration, non-functional, and control items with acceptance criteria, across three parts: Part 1 (foundation F1–F6 + ACH), Part 2 (Fedwire + RTP, with real-time AML/SAR/FinCEN), and Part 3 (SWIFT + stablecoin). A discovery-grade specification covers the stablecoin rail given its novelty and external dependencies.

# 10. Prioritization & calibration

A Phase 0 calibration model scores every initiative on volume × risk × feasibility with configurable weights and wave thresholds, and compares the model-suggested sequence against the planned roadmap, flagging divergences to reconcile. Populated with real volumes, break and false-positive rates, and risk assessments, it converts judgment into a data-driven sequence.

# 11. Business case

The value comes from four levers, in priority order for this program:

- Risk reduction. One real-time screening spine and consistent AML/SAR coverage reduce sanctions, fraud, and regulatory exposure — the dominant driver on irrevocable rails.

- Cost. An exception-based model and engineered-down false positives cut manual touch and cost per payment.

- Resilience & scale. STP and shared services absorb volume — and 24/7 instant-rail demand — without linear headcount.

- Readiness. A common platform makes new rails (e.g., stablecoin) and new volumes additive rather than another silo.

# 12. Regulatory assurance

Controls are embedded and mapped to obligations: OFAC sanctions (block/reject and report), BSA/AML monitoring and SAR/CTR filing, the BSA and crypto Travel Rules, Reg E (ACH consumer), Reg J / UCC 4A (Fedwire), NACHA rules (ACH), and the evolving federal stablecoin framework. Every obligation maps to a named capability, is monitored in real time where the rail demands it, and is fully audited and retained.

# 13. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| Reference & list data quality | Build golden reference and sanctions data (F1) first; stewardship and versioning. |
| Real-time screening on irrevocable rails | Prove pre-send screening on Fedwire (business hours) before RTP (24/7); latency budgets and tuning. |
| Vendor / network dependency | Manage analytics, Travel Rule, custody, and operator relationships as governed dependencies. |
| Regulatory uncertainty (stablecoin) | Start discovery early; confirm the legal position before build; design for change. |
| Change management | Phased transition with reskilling from re-keying to exception and alert clearing. |
| RPA brittleness | Use RPA only to bridge portals; mandate a decommission path for each. |

# 14. Governance & investment

A single payments operations product owner governs the canonical lifecycle and shared services; a steering committee owns the roadmap, prioritization, and aged-exception/alert review. Build-vs-buy is deliberate: buy or partner for commoditized capability (screening engines, analytics, Travel Rule, SWIFT connectivity, on-chain infrastructure, operator and correspondent rails), and build the orchestration, reference-data, reconciliation, and control layers that differentiate. Investment is staged by wave, with Phase 0 a low-cost step that de-risks everything downstream.

# 15. The ask & next steps

- Approve the program, the exception-based operating model, and the four-wave sequence.

- Run Phase 0 calibration — populate real volumes, false-positive and break rates, and risk assessments.

- Fund the Wave 0 foundation — the screening spine, golden data, the payment hub, the exceptions desk, reconciliation, and AML/SAR.

- Authorize stablecoin discovery to begin in parallel, given its long lead time.

Decision requested. Approval to proceed and to commence Phase 0.